## Actual
El Proyecto Estufa Finca The Farm Stove Pilot Project
|  | Nov 2010 | [29 empty] | Dec 2010 | [30 empty] | Jan 2011 | [30 empty] | Feb 2011 | [27 empty] | Mar '11 | [30 empty] | Apr '11 | [29 empty] | May '11
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
|  | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T
USA | bar: Nov 2010 6 S; Nov 2010 13 S; Nov 2010 20 S; Nov 2010 25 T; Nov 2010 27 S; Dec 2010 4 S; Dec 2010 11 S; Dec 2010 18 S; Jan 2011 8 S; Jan 2011 15 S; Jan 2011 22 S; Jan 2011 29 S; Feb 2011 5 S; Feb 2011 12 S; Feb 2011 19 S; Feb 2011 26 S; Mar '11 5 S; Mar '11 12 S; Mar '11 19 S; Mar '11 26 S; Apr '11 2 S; Apr '11 9 S; Apr '11 16 S; Apr '11 23 S; Apr '11 30 S; May '11 7 S; May '11 14 S; May '11 21 S; May '11 28 S
COSTA RICA
| LABOR | Feb 2011 21 M: Total
[23 empty] | Art |  |  |  |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 8 | 8 | 8 | 12 | 12 | 10 | 10 | 10 | 12 | 12 | 12 | 10 | 8 | 4 | 10 | [34 empty] | 468
[23 empty] | Susan | [22 empty] | 8 | 8 | 8 | 8 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 10 | 10 | 4 | [53 empty] | 134
[23 empty] | Tom | [26 empty] | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 10 | 10 | 10 | 10 | 10 | 10 | 8 | [49 empty] | 146
[23 empty] | Willy | [27 empty] | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 |  | 8 |  | 8 | 8 | 8 | 8 | 8 | 8 |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | [34 empty] | 192
[23 empty] | Arturo | [26 empty] | 8 | [8 empty] | 4 | [54 empty] | 12
[23 empty] | Carolina | [40 empty] | 6 | [49 empty] | 6
[23 empty] | Diego | [35 empty] | 4 | [54 empty] | 4
[23 empty] | Evelyn | [26 empty] | 8 | 8 | 8 | [61 empty] | 24
[23 empty] | Diana | [26 empty] | 8 | 8 | 8 | [61 empty] | 24
0
0
0
[113 empty] | Total | 1010
Ptnr Indoor Air Forum (Lima)
SeaChar/APORTES meeting
Stakeholders meeting
Project Planning
- Identify: - Workflow, schedule, plan - Budget - Housing - Transporatation - Fuel - Supplies - Tools - Equipment - Stove materials - Stove housing materials - Permits - - - - -
Planning schedule available to send to outside groups
Prepare for: Orientation meetings - Major stakeholder - Families - Volunteers - Foundations - Report materials - Stove workshop -
Preparation
Group A Follow-up Surveys
-Acquire and supply: - Fuel - Supplies - Tools - Equipment - Stove materials - Stove housing materials - Permits - Housing -Transportation - - -
-Select: - 50 families total - 15 families Group A - 15 families Group B
Stove workshop Fundraiser
Development / Fundraising/Communication
Donor/volunteer engagement - Thank yous - Updates - Photos - Blog
Fundraising - Grants - Individual - Product based
Communication - Website - Take-away materials - Photo-s/video
Report Development
Stove workshop Fundraiser
Appeal letter
Appeal letter mtg
Sched mtg
Sched mtg
Sched mtg
Report Complete
Michelle Fritts Seattle Foundation
Stove workshop Thank you letter
Grant deadline Global Health Initiative
Art Donnelly arrives
Work with APORTES in shop
Meet with UNA, M. Fritts, Diego
APORTES planning meeting
Work with APORTES
UNA meeting
Susan Bolton arrrives
Tom Ternes arrives
Dan Foster and family arrives
Controlled Cooking Test Initial Survey
Art Donnelly leaves
Meeting with APORTES women
Group A (16) Install settings, interviews, stove lighting workshops
Group B (16) Install settings, interviews, stove lighting workshops
Tom Ternes leaves
Susan Bolton leaves
Group B Follow-up Surveys
Controlled Cooking Test Follow up Survey
Initial raw interview data released
Follow-up raw interview data released
Costa Rica Rotary Intl Meeting
DePaul University Workshops
cd
Feliz Navidad Appeal
Seattle Intl Grant awarded
Additional Follow-up Surveys (if reqd)
cd
cd
cd
cd
cd

## Plan
El Proyecto Estufa Finca The Farm Stove Pilot Project
|  | Nov 2010 | [29 empty] | Dec 2010 | [30 empty] | Jan 2011 | [30 empty] | Feb 2011 | [27 empty] | Mar '11 | [30 empty] | Apr '11 | [29 empty] | May '11
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
|  | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T
USA | bar: Nov 2010 6 S; Nov 2010 13 S; Nov 2010 20 S; Nov 2010 25 T; Nov 2010 27 S; Dec 2010 4 S; Dec 2010 11 S; Dec 2010 18 S; Jan 2011 8 S; Jan 2011 15 S; Jan 2011 22 S; Jan 2011 29 S; Feb 2011 5 S; Feb 2011 12 S; Feb 2011 19 S; Feb 2011 26 S; Mar '11 5 S; Mar '11 12 S; Mar '11 19 S; Mar '11 26 S; Apr '11 2 S; Apr '11 9 S; Apr '11 16 S; Apr '11 23 S; Apr '11 30 S; May '11 7 S; May '11 14 S; May '11 21 S; May '11 28 S
COSTA RICA
LABOR
Tom
Ptnr Indoor Air Forum (Lima)
SeaChar/APORTES meeting
Stakeholders meeting
Project Planning
- Identify: - Workflow, schedule, plan - Budget - Housing - Transporatation - Fuel - Supplies - Tools - Equipment - Stove materials - Stove housing materials - Permits - - - - -
Planning schedule available to send to outside groups
Prepare for: Orientation meetings - Major stakeholder - Families - Volunteers - Foundations - Report materials - Stove workshop -
Preparation
Group A Baseline Fuel Monitor
Group A Stove installation (15 families)
Group A New Stove Fuel Monitor
-Acquire and supply: - Fuel - Supplies - Tools - Equipment - Stove materials - Stove housing materials - Permits - Housing -Transportation - - -
-Select: - 50 families total - 15 families Group A - 15 families Group B
Stove workshop Fundraiser
Development / Fundraising/Communication
Donor/volunteer engagement - Thank yous - Updates - Photos - Blog
Fundraising - Grants - Individual - Product based
Communication - Website - Take-away materials - Photo-s/video
Report Development
Stove workshop Fundraiser
Art
(Peru)
Project Monitoring
- Schedule - Budget
Appeal letter
Appeal letter mtg
Sched mtg
Sched mtg
Vacation?
Sched mtg
Preliminary Report complete
Final Report
Michelle Fritts Seattle Foundation
Stove workshop Thank you letter
Grant deadline Global Health Initiative
Dan Foster + family
Group A Registration/ Baseline Survey 3 teams
Art Donnelly arrives
Work with APORTES in shop
Meet with UNA, M. Fritts, Diego
APORTES planning meeting
Diego arrives
Work with APORTES
UNA meeting
Susan Bolton arrrives
Tom Ternes arrives
Group B Baseline Fuel Monitor
Group B Stove installation (15 families)
Group B New Stove Fuel Monitor
Group B Registration/ Baseline Survey 3 teams
Dan Foster (+2) arrives
Group A Customer Satisfaction Survey
Group B Customer Satisfaction Survey
Art Donnelly leaves